## 82Q - PROJECT
Project_Name | Project_Number | GC_Name | GC_Contact | Address | Start_Date | End_Date | Stage
PS 082K | 30000 | Technico Construction | Ramesh Kalirangaswamy | 25-39 Borden Avenue LIC, NY 11101 | 2025-12-15 | 2026-11-05 | Fabrication

## 82Q - PRIME_CONTRACTS
Contract_ID | GC_Name | GC_Contact_Name | GC_Contact_Email | GC_Contact_Phone | Original_Contract_Value | Start_Date | End_Date | Payment_Terms (e.g. Net 30, Net 60) | Contract Document Link (OneDrive URL) | Contract Scheduled Document Link (OneDrive or PDF)
C000080829 | Technico Construction | Ramesh Kalirangaswamy | RameshK@technico-csi.com | (718) 937-3800 | 435000 | 2025-12-15 | 2026-11-05 | Net 60 | https://www.dropbox.com/scl/fo/m09jrtziezzi79516yg7d/ALvsIwZrBII-GxNOBEqEQfc/IS%2082K/PS%2082K.pdf?rlkey=2gle93ap7ug1j7ugx22xk0pxj&st=4mkb3xtt&dl=0 | https://www.dropbox.com/scl/fo/m09jrtziezzi79516yg7d/AGnxpR0LutBwdcYkwJmBknc/IS%2082K/IS%2082K_Schedule_Baseline_05.12.2025%20.pdf?rlkey=2gle93ap7ug1j7ugx22xk0pxj&st=55pjcbjg&dl=0

## 82Q - PRIME_COs
CO_ID | Name | Description | Status | Amount (auto) | Reason | Schedule_Impact_Days | Markup_Pct (e.g. 10 = 10%) | Total_CO_Amount (auto) | Creator | Assignee | Due_Date | Approval_Date | Document_Link

## 82Q - PRIME_CO_LINE_ITEMS
CO_ID | Category | Cost_Code | Item | Qty | Unit_Type | Unit_Price | Price (Qty × Unit_Price)

## 82Q - RFQs
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Title | Vendor | Status | Final_Amount | Issued Date
30000 | PS 082K | RFQ-2025-1458 | MATERIAL REQUEST FORM | QSS ¦ ASST
30000 | PS 082K | RFQ-2025-1459 | MATERIAL REQUEST FORM | QSS ¦ ASST
30000 | PS 082K | RFQ-2025-1614 | MATERIAL REQUEST FORM | Senhao
30000 | PS 082K | RFQ-2025-1630 | MATERIAL REQUEST FORM | Rynone

## 82Q - RFQ_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Item | Unit | Qty | Unit_Price
30000 | PS 082K | RFQ-2025-1458 | Vanities - Daltile Lincoln White NQ59
30000 | PS 082K | RFQ-2025-1459 | Windowsills - Wilsonart Frosty White
30000 | PS 082K | RFQ-2025-1614 | Movables with Doors and PL | EA | 3
30000 | PS 082K | RFQ-2025-1614 | Movables with Tops | EA | 130
30000 | PS 082K | RFQ-2025-1614 | Student Wardrobes | EA | 20
30000 | PS 082K | RFQ-2025-1614 | Tall Bookshelves | EA | 4
30000 | PS 082K | RFQ-2025-1614 | Wall Hungs | EA | 103
30000 | PS 082K | RFQ-2025-1630 | Plastic laminate tops

## 82Q - RFQ_ATTACHMENTS
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Document_Name | Document_Link
30000 | PS 082K | RFQ-2025-1458
30000 | PS 082K | RFQ-2025-1459
30000 | PS 082K | RFQ-2025-1614
30000 | PS 082K | RFQ-2025-1630

## 82Q - PURCHASE_ORDERS
PROJECT NUMBER | PROJECT NAME | PO_ID | Linked_RFQ_ID (optional) | Issue_Date | Status | Vendor | Trade | PO_Amount | Tax_Rate | Expected_Date | Delivery_Date | Payment_Terms (e.g. Net 30) | Lead_Time | Ship_To | Notes | Created_By | Document_Link
30000 | PS 082K | 24850 |  | 2024-12-26 | CLOSED | WW Shop Drawings | SCA | 4150 | [5 empty] | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Mahavir
30000 | PS 082K | 24923 |  | 2025-01-21 |  | AK International | SCA | 118500 | [5 empty] | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Tomasz
30000 | PS 082K | 25433-1 |  | 2025-07-02 | CLOSED | Ives Hinges | SCA | 94.72 |  |  | 2025-07-11 |  |  | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Mahavir
30000 | PS 082K | 25636-3 |  | 2025-09-15 | CLOSED | Xuzhou Baoqi Wood | SCA | 13434.5 |  |  | 2025-11-15 |  |  | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Tomasz
30000 | PS 082K | 25768 |  | 2025-08-25 | CLOSED | Xuzhou Baoqi Wood | SCA | 47311.53 | [5 empty] | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Tomasz
30000 | PS 082K | 26042 |  | 2026-02-12 |  | Atlantic Plywood | SCA | 136.25 |  |  | 2026-02-12 |  |  | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Mahavir

## 82Q - PO_LINE_ITEMS
| PROJECT NAME | PO_ID | Item | Qty | Unit | Unit_Price | Price (Qty × Unit_Price)
30000 | PS 082K | 24850 | Fabrication of shop drawings | 1 |  | 4000 | 4000
30000 | PS 082K | 24850 | Benches in the 2nd, 3rd, and 4th levels. | 1 |  | 150 | 150
30000 | PS 082K | 24923 | Installation - This proposal is intended to furnish the installation of millwork according to highlighted drawings provided, FF 101, 102, 103, 104, 105, A-211 (Front Stage & Trim) | 1 |  | 118500 | 118500
30000 | PS 082K | 25433-1 | Ives 581 A92 Aluminum | 50 |  | 1.59 | 79.5
30000 | PS 082K | 25433-1 | Shipping | 1 |  | 7.5 | 7.5
30000 | PS 082K | 25433-1 | Tax | 1 |  | 7.72 | 7.72
30000 | PS 082K | 25636-3 | PO 25636 - Multiple SCA - Splitted into 4 projects | 1 |  | 13434.5 | 13434.5
30000 | PS 082K | 25768 | Bookshelves Cabinets - 36x12x28 - Red Oak with PL (Wilsonar #7938) | 3 |  | 207.83 | 623.49
30000 | PS 082K | 25768 | Movables - 36x12x28 Red Oak with PL (Wilsonart #7938) | 130 |  | 179.93 | 23390.9
30000 | PS 082K | 25768 | Student Wardrobe - 38x14x33, Red Oak | 6 |  | 204 | 1224
30000 | PS 082K | 25768 | Student Wardrobe - 48x14x33, Red Oak | 14 |  | 240 | 3360
30000 | PS 082K | 25768 | Tall Bookshelves - 24x18x84, Red Oak | 2 |  | 302.51 | 605.02
30000 | PS 082K | 25768 | Tall Bookshelves - 48x18x84, Red Oak | 2 |  | 539.06 | 1078.12
30000 | PS 082K | 25768 | Wall Hung - 24x12x24, Red Oak | 24 |  | 146 | 3504
30000 | PS 082K | 25768 | Wall Hung - 29x12x24, Red Oak | 10 |  | 152 | 1520
30000 | PS 082K | 25768 | Wall Hung - 30x12x24, Red Oak | 6 |  | 152 | 912
30000 | PS 082K | 25768 | Wall Hung - 34x12x24, Red Oak | 57 |  | 176 | 10032
30000 | PS 082K | 25768 | Wall Hung - 36x12x24, Red Oak | 6 |  | 177 | 1062
30000 | PS 082K | 26042 | Shelf Center Rest Steel Zinc 186/187 Brackets ea | 500 |  | 0.25 | 125
30000 | PS 082K | 26042 | Handling | 1 |  | 11.25 | 11.25

## 82Q - PO_PAYMENTS
PROJECT NUMBER | PROJECT NAME | PO_ID | Date | CHK# | Note | Amount
30000 | PS 082K | 24850 | 2025-01-11 | 5277 | Check # 5277 | 1000
30000 | PS 082K | 24850 | 2025-03-14 | 1031 | SCA Check # 1031 | 2000
30000 | PS 082K | 24850 | 2025-04-16 | 1066 | SCA Check # 1066 | 1150
30000 | PS 082K | 25433-1 | 2025-07-02 |  | Amex | 94.72
30000 | PS 082K | 25636-3 | 2025-10-09 |  | Wired 10/9/25 | 4030.35
30000 | PS 082K | 25636-3 | 2026-01-30 |  | Wired 01/30/26 | 2145.15
30000 | PS 082K | 25636-3 | 2026-03-04 |  | Wired 3/04/26 | 7259
30000 | PS 082K | 25768 | 2025-11-12 |  | Wired 11/12/25 | 14193.46
30000 | PS 082K | 25768 | 2025-11-21 |  | Wired 11/21/25 | 27274.31
30000 | PS 082K | 25768 | 2026-03-04 |  | Wired 3/04/26 | 6033.48

## 82Q - PO_CHANGE_ORDERS
PROJECT NUMBER | PROJECT NAME | PO_ID | PO_CO_ID | Name | Description | Status | Amount | Reason | Schedule_Impact_Days | Markup_Pct | Creator | Assignee | Due_Date | Approval_Date | Document_Link
30000 | PS 082K | 25768 | 25768-CO1 |  | Change order per payment tracking |  | 189.72 |  |  |  | Tomasz

## 82Q - PO_CO_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | PO_CO_ID | Category | Cost_Code | Item | Qty | Unit_Type | Unit_Price | Price (Qty × Unit_Price)
30000 | PS 082K | 25768-CO1 |  |  | Change order adjustment | 1 |  | 189.72 | 189.72