## EASTERN - PROJECT
Project_Name | Project_Number | GC_Name | GC_Contact | Address | Start_Date | End_Date | Stage
Eastern Parkway Library | 31500 | MPCC Corp. | lou@mpcccorp.com | 81 Rockdale Avenue New Rochelle, NY 10801 | 2025-12-24 | 2027-07-22 | Submitals

## EASTERN - PRIME_CONTRACTS
Contract_ID | GC_Name | GC_Contact_Name | GC_Contact_Email | GC_Contact_Phone | Original_Contract_Value | Start_Date | End_Date | Payment_Terms (e.g. Net 30, Net 60) | Contract Document Link (OneDrive URL) | Contract Scheduled Document Link (OneDrive or PDF)
20258808907 | MPCC Corp. | Louis Calicchia | lou@mpcccorp.com | 914636-0000 | 800000 | 2025-12-24 | 2027-07-22 | Net 90 | https://www.dropbox.com/scl/fo/m09jrtziezzi79516yg7d/AM2LYRTxVIKvyyLchiyoiC0/Eastern%20Parkway/EASTERN%20PKWAY.pdf?rlkey=2gle93ap7ug1j7ugx22xk0pxj&st=syrh1cno&dl=0 | https://www.dropbox.com/scl/fo/m09jrtziezzi79516yg7d/AP7XvJGrIZdI3a4D7xSimQo/Eastern%20Parkway/Appendix%201%20-%20LBM18EPOH%20-%20Baseline%20Schedule%20Rev.01%20-%20Activity%20Details.pdf?rlkey=2gle93ap7ug1j7ugx22xk0pxj&st=tvf6twa8&dl=0

## EASTERN - PRIME_COs
CO_ID | Name | Description | Status | Amount (auto) | Reason | Schedule_Impact_Days | Markup_Pct (e.g. 10 = 10%) | Total_CO_Amount (auto) | Creator | Assignee | Due_Date | Approval_Date | Document_Link
06400-0001 | Library Stack System | Furnish & install metal shelving (MOS) | Approved | 86000 |  |  |  | 86000 | Peter Ligas | Sebastian Woskolej |  | 2026-02-09

## EASTERN - PRIME_CO_LINE_ITEMS
CO_ID | Category | Cost_Code | Item | Qty | Unit_Type | Unit_Price | Price (Qty × Unit_Price)
06400-0001 |  |  | Library Stack System | 1 | LS | 86000 | 86000

## EASTERN - RFQs
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Title | Vendor | Status | Final_Amount | Issued Date
31500 | Eastern Parkway Library | RFQ-2025-1620 | Office Systems - Previous Quote Reference | Modern Office Systems
31500 | Eastern Parkway Library | RFQ-2025-1626 | Shelving System Distribution | MJ Shelving System Distributors

## EASTERN - RFQ_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Item | Unit | Qty | Unit_Price
31500 | Eastern Parkway Library | RFQ-2025-1620 | Previous quote reference 1.6.2025
31500 | Eastern Parkway Library | RFQ-2025-1626

## EASTERN - RFQ_ATTACHMENTS
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Document_Name | Document_Link
31500 | Eastern Parkway Library | RFQ-2025-1620
31500 | Eastern Parkway Library | RFQ-2025-1626

## EASTERN - PURCHASE_ORDERS
PROJECT NUMBER | PROJECT NAME | PO_ID | Linked_RFQ_ID (optional) | Issue_Date | Status | Vendor | Trade | PO_Amount | Tax_Rate | Expected_Date | Delivery_Date | Payment_Terms (e.g. Net 30) | Lead_Time | Ship_To | Notes | Created_By | Document_Link
31500 | Eastern Parkway Library | 25783 |  | 2025-10-27 | CLOSED | Woodwork Shop Drawings LLC | Civil | 4000 |  |  | 2025-12-29 |  |  | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Sebastian
31500 | Eastern Parkway Library | 26054 |  | 2026-03-03 | OPEN | Modern Office Systems, LLC | Civil | 69135 | [5 empty] | Eastern Library | Please advise minimum 1 day before delivery to ensure Loading Dock availability. | Peter

## EASTERN - PO_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | PO_ID | Item | Qty | Unit | Unit_Price | Price (Qty × Unit_Price)
31500 | Eastern Parkway Library | 25783 | Produce millwork shop drawings for BPL Eastern Parkway Renovation & Expansion project | 1 |  | 4000 | 4000
31500 | Eastern Parkway Library | 26054 | Furnish and install Library Stack System / Cantilever Shelving | 1 |  | 69135 | 69135
31500 | Eastern Parkway Library | 26054 | As per quote #2059-26760
31500 | Eastern Parkway Library | 26054 | As per highlighted drawings & specifications

## EASTERN - PO_PAYMENTS
PROJECT NUMBER | PROJECT NAME | PO_ID | Date | CHK# | Note | Amount
31500 | Eastern Parkway Library | 25783 | 2025-12-06 | 1177 | Civil Check #1177 | 2000
31500 | Eastern Parkway Library | 25783 | 2026-01-23 | 1227 | Civil Check #1227 | 2250

## EASTERN - PO_CHANGE_ORDERS
PROJECT NUMBER | PROJECT NAME | PO_ID | PO_CO_ID | Name | Description | Status | Amount | Reason | Schedule_Impact_Days | Markup_Pct | Creator | Assignee | Due_Date | Approval_Date | Document_Link
31500 | Eastern Parkway Library | 25783 | 25783-01 | CO for WW Shop Drawings | Millwork shop drawings for Eastern Parkway Library Vestibule 100 wall panel drawings |  | 250 | [5 empty] | 2025-11-07

## EASTERN - PO_CO_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | PO_CO_ID | Category | Cost_Code | Item | Qty | Unit_Type | Unit_Price | Price (Qty × Unit_Price)
31500 | Eastern Parkway Library | 25783-01 | Materials | — | Millwork shop drawings for Eastern Parkway Library Vestibule 100 wall panel drawings | 1 | LS | 250 | 250