## REQ2
Elli NY Design Corp. | [6 empty] | Requisition No. | #001 | SCA REQUISITION & CERTIFICATE FOR PAYMENT
Project: |  | 489 State Street - School |  |  |  |  | Hunter Roberts Construction Group. LLC |  | TO: | Hunter Roberts Construction Group, LLC |  |  | PROJECT NAME: 489 State Street School |  |  |  | REQUISTION & CERTIFICATE NO: | #001
|  | 489 State Street Brooklyn NY 11217 |  |  |  | Contractor: |  |  |  | 55 Water Street, 51st Floor
[10 empty] | New York, NY 10041 | [6 empty] | AS OF:
|  | DESCRIPTION | TOTAL | Percentage | Total from | Total Completed | Total | TOTAL
|  |  |  | Completed | Previous | To Date | Remaining | for Period | FROM (SUB) CONTRATOR: |  | Elli NY Design Corp. | [5 empty] | CONTRACT NO: | 230200-BP09
| Spec | [7 empty] | ADDRESS |  | 50-01 Metropolitan Ave.
| All | Shop Drawings | 50000 | 0% | 0 | 0 | 50000 | 0 |  |  | Ridgewood, NY 11385 | [5 empty] | DATE PREPARED: | 2026-01-15
| All | Submittals / Samples | 26000 | 0% | 0 | 0 | 26000 | 0 | CONTRACT FOR (TRADE): |  | Millwork | (06410/06200)
| All | Mock Up Room | 14000 | 0% | 0 | 0 | 14000 | 0 | [5 empty] | Application is made for Payment, as shown below, in connection with the Contract.
| All | Shop Mobilization | 18000 | 0% | 0 | 0 | 18000 | 0 | [5 empty] | Trade Payment Breakdown is attached
| All | Field Mobilization | 8000 | 0% | 0 | 0 | 8000 | 0 | CHANGE ORDER SUMMARY
|  | Total For 06200: | 116000 | 0% | 0 | 0 | 116000 | 0 | Change Orders approved in previous months by Owner
[6 empty] | . | [7 empty] | 1. ORIGINAL CONTRACT SUM………………………… |  |  |  | 996000
Material | 06200 | Cellar: Stage / Proscenium Wood Panels, Stairs, Trim, Barres | 36000 | 0% | 0 | 0 | 36000 | 0
Labor | 06200 | Cellar: Stage / Proscenium Wood Panels, Stairs, Trim, Barres | 14000 | 0% | 0 | 0 | 14000 | 0 |  |  | Approved | Pending |  | 2. Net change by Change Orders (LINE +) ………………….. |  |  |  | 0
Material | 06410 | Cellar: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0 | Approved this Month |  |  |  |  | 3. CONTRACT SUM TO DATE |  |  |  | 996000
Labor | 06410 | Cellar: Lavatory Countertops | 4000 | 0% | 0 | 0 | 4000 | 0 | Number | Description |  |  |  | 4. TOTAL COMPLETED TO DATE …………………….. |  |  |  | 0
Material | 06410 | Cellar: Bench | 4500 | 0% | 0 | 0 | 4500 | 0 |  |  | 0 | 0
Labor | 06410 | Cellar: Bench | 1500 | 0% | 0 | 0 | 1500 | 0 |  |  | 0 | 0 |  | 5. RETAINAGE:
Material | 06410 | 1st Floor: Custom Desks | 45000 | 0% | 0 | 0 | 45000 | 0 |  |  | 0 | 0 |  | 10% | of Completed Work | 0
Labor | 06410 | 1st Floor: Custom Desks | 10000 | 0% | 0 | 0 | 10000 | 0 |  |  | 0 | 0 |  |  | (Column D + E)
Material | 06410 | 1st Floor: Wood Cabinetry | 4500 | 0% | 0 | 0 | 4500 | 0 |  |  | 0 | 0 |  | Total Retainage (Line 5a + 5b or
Labor | 06410 | 1st Floor: Wood Cabinetry | 2500 | 0% | 0 | 0 | 2500 | 0 |  |  | 0 | 0 |  | Total in Column 1) …………………………… |  |  |  | 0
Material | 06410 | 1st Floor: Countertops | 1800 | 0% | 0 | 0 | 1800 | 0 |  |  | 0 | 0 |  | 6. TOTAL EARNED LESS RETAINAGE …………………. |  |  |  | 0
Labor | 06410 | 1st Floor: Countertops | 1200 | 0% | 0 | 0 | 1200 | 0 |  |  | 0 | 0 |  |  | (Line 4 less Line 5 Total)
Material | 06410 | 2nd Floor: Lavatory Countertops | 27000 | 0% | 0 | 0 | 27000 | 0 |  |  | 0 | 0 |  | 7. TOTAL PREVIOUS CERTIFICATES FOR PAYMENT |  |  |  | 0
Labor | 06410 | 2nd Floor: Lavatory Countertops | 8000 | 0% | 0 | 0 | 8000 | 0 |  |  | 0 | 0 |  |  | (Line 6 from prior Requistion)………………
Material | 06410 | 3rd Floor: Wood Cabinetry | 27000 | 0% | 0 | 0 | 27000 | 0 |  |  | 0 | 0 |  | 8. CURRENT PAYMENT DUE …………………………………. |  |  |  | 0
Labor | 06410 | 3rd Floor: Wood Cabinetry | 11000 | 0% | 0 | 0 | 11000 | 0 |  |  | 0 | 0 |  | 9. BALANCE TO FINISH, PLUS RETAINAGE ………………… |  |  |  | 996000
Material | 06410 | 3rd Floor: Countertops | 18000 | 0% | 0 | 0 | 18000 | 0 | Net by Change Orders |  | 0 |  |  |  | (Line 3 less Line 6)
Labor | 06410 | 3rd Floor: Countertops | 10000 | 0% | 0 | 0 | 10000 | 0 | SUB-CONTRACTOR AUTHORIZED OFFICER SIGNATURE: |  |  |  |  | GENERAL CONTRACTOR AUTHORIZED AMOUNT |  |  | _____________________
Material | 06410 | 3rd Floor: Closet interiors | 9000 | 0% | 0 | 0 | 9000 | 0 | BY: | Tomasz Bartosiak |  | Senior Project Manager |  |  | APPROVED BY: ______________________________________
Labor | 06410 | 3rd Floor: Closet interiors | 5000 | 0% | 0 | 0 | 5000 | 0 |  | Tomasz Bartosiak |  | TITLE
Material | 06410 | 4th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 4th Floor: Lavatory Countertops | 4000 | 0% | 0 | 0 | 4000 | 0
Material | 06410 | 4th Floor: Wood Cabinetry | 49500 | 0% | 0 | 0 | 49500 | 0
Labor | 06410 | 4th Floor: Wood Cabinetry | 20500 | 0% | 0 | 0 | 20500 | 0
Material | 06410 | 4th Floor: Countertops | 36000 | 0% | 0 | 0 | 36000 | 0
Labor | 06410 | 4th Floor: Countertops | 19000 | 0% | 0 | 0 | 19000 | 0
Material | 06410 | 4th Floor: Closet interiors | 18000 | 0% | 0 | 0 | 18000 | 0
Labor | 06410 | 4th Floor: Closet interiors | 7000 | 0% | 0 | 0 | 7000 | 0
Material | 06410 | 4th Floor: Benches | 9000 | 0% | 0 | 0 | 9000 | 0
Labor | 06410 | 4th Floor: Benches | 3000 | 0% | 0 | 0 | 3000 | 0
Material | 06410 | 5th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 5th Floor: Lavatory Countertops | 4000 | 0% | 0 | 0 | 4000 | 0
Material | 06410 | 5th Floor: Wood Cabinetry | 49500 | 0% | 0 | 0 | 49500 | 0
Labor | 06410 | 5th Floor: Wood Cabinetry | 20500 | 0% | 0 | 0 | 20500 | 0
Material | 06410 | 5th Floor: Countertops | 31500 | 0% | 0 | 0 | 31500 | 0
Labor | 06410 | 5th Floor: Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Material | 06410 | 5th Floor: Closet interiors | 18000 | 0% | 0 | 0 | 18000 | 0
Labor | 06410 | 5th Floor: Closet interiors | 7000 | 0% | 0 | 0 | 7000 | 0
Material | 06410 | 5th Floor: Benches | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 5th Floor: Benches | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 6th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 6th Floor: Lavatory Countertops | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 6th Floor: Wood Cabinetry | 31500 | 0% | 0 | 0 | 31500 | 0
Labor | 06410 | 6th Floor: Wood Cabinetry | 13500 | 0% | 0 | 0 | 13500 | 0
Material | 06410 | 6th Floor: Countertops | 18000 | 0% | 0 | 0 | 18000 | 0
Labor | 06410 | 6th Floor: Countertops | 7000 | 0% | 0 | 0 | 7000 | 0
Material | 06410 | 6th Floor: Closet interiors | 9000 | 0% | 0 | 0 | 9000 | 0
Labor | 06410 | 6th Floor: Closet interiors | 6000 | 0% | 0 | 0 | 6000 | 0
Material | 06410 | 6th Floor: Benches | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 6th Floor: Benches | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 7th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 7th Floor: Lavatory Countertops | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 7th Floor: Wood Cabinetry | 28800 | 0% | 0 | 0 | 28800 | 0
Labor | 06410 | 7th Floor: Wood Cabinetry | 13200 | 0% | 0 | 0 | 13200 | 0
Material | 06410 | 7th Floor: Countertops | 16200 | 0% | 0 | 0 | 16200 | 0
Labor | 06410 | 7th Floor: Countertops | 6800 | 0% | 0 | 0 | 6800 | 0
Material | 06410 | 7th Floor: Closet interiors | 9000 | 0% | 0 | 0 | 9000 | 0
Labor | 06410 | 7th Floor: Closet interiors | 6000 | 0% | 0 | 0 | 6000 | 0
Material | 06410 | 7th Floor: Benches | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 7th Floor: Benches | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 8th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 8th Floor: Lavatory Countertops | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 8th Floor: Benches | 18000 | 0% | 0 | 0 | 18000 | 0
Labor | 06410 | 8th Floor: Benches | 4500 | 0% | 0 | 0 | 4500 | 0
|  | Total For 06410: | 880000 | 0% | 0 | 0 | 880000 | 0
|  | Line Totals | 996000 | 0% | 0 | 0 | 996000 | 0
11250
Contract Value
450000
Material |  | Labor
364500 |  | 67500
81.1749
81.1749