## REQ2
Elli NY Design Corp. | [6 empty] | Requisition No. | SOV | SCA REQUISITION & CERTIFICATE FOR PAYMENT
Project: |  | 489 State Street - School |  |  |  |  | Hunter Roberts Construction Group. LLC |  | TO: | Hunter Roberts Construction Group, LLC |  |  | PROJECT NAME: 489 State Street School |  |  |  | REQUISTION & CERTIFICATE NO: | SOV
|  | 489 State Street Brooklyn NY 11217 |  |  |  | Contractor: |  |  |  | 55 Water Street, 51st Floor
[10 empty] | New York, NY 10041 | [6 empty] | AS OF:
|  | DESCRIPTION | TOTAL | Percentage | Total from | Total Completed | Total | TOTAL
|  |  |  | Completed | Previous | To Date | Remaining | for Period | FROM (SUB) CONTRATOR: |  | Elli NY Design Corp. | [5 empty] | CONTRACT NO: | 230200-BP09
| Spec | [7 empty] | ADDRESS |  | 50-01 Metropolitan Ave.
| All | Shop Drawings | 50000 | 0% | 0 | 0 | 50000 | 0 |  |  | Ridgewood, NY 11385 | [5 empty] | DATE PREPARED: | 2021-10-07
| All | Submittals / Samples | 26000 | 0% | 0 | 0 | 26000 | 0 | CONTRACT FOR (TRADE): |  | Millwork | (06410/06200)
| All | Mock Up Room | 14000 | 0% | 0 | 0 | 14000 | 0 | [5 empty] | Application is made for Payment, as shown below, in connection with the Contract.
| All | Shop Mobilization | 18000 | 0% | 0 | 0 | 18000 | 0 | [5 empty] | Trade Payment Breakdown is attached
| All | Field Mobilization | 8000 | 0% | 0 | 0 | 8000 | 0 | CHANGE ORDER SUMMARY
|  | Total For 06200: | 116000 | 0% | 0 | 0 | 116000 | 0 | Change Orders approved in previous months by Owner
[6 empty] | . | [7 empty] | 1. ORIGINAL CONTRACT SUM………………………… |  |  |  | 996000
Material | 06200 | Cellar: Stage / Proscenium Wood Panels, Stairs, Trim, Barres | 36000 | 0% | 0 | 0 | 36000 | 0
Labor | 06200 | Cellar: Stage / Proscenium Wood Panels, Stairs, Trim, Barres | 14000 | 0% | 0 | 0 | 14000 | 0 |  |  | Approved | Pending |  | 2. Net change by Change Orders (LINE +) ………………….. |  |  |  | 0
Material | 06410 | Cellar: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0 | Approved this Month |  |  |  |  | 3. CONTRACT SUM TO DATE |  |  |  | 996000
Labor | 06410 | Cellar: Lavatory Countertops | 4000 | 0% | 0 | 0 | 4000 | 0 | Number | Description |  |  |  | 4. TOTAL COMPLETED TO DATE …………………….. |  |  |  | 0
Material | 06410 | Cellar: Bench | 4500 | 0% | 0 | 0 | 4500 | 0 |  |  | 0 | 0
Labor | 06410 | Cellar: Bench | 1500 | 0% | 0 | 0 | 1500 | 0 |  |  | 0 | 0 |  | 5. RETAINAGE:
Material | 06410 | 1st Floor: Custom Desks | 45000 | 0% | 0 | 0 | 45000 | 0 |  |  | 0 | 0 |  | 10% | of Completed Work | 0
Labor | 06410 | 1st Floor: Custom Desks | 10000 | 0% | 0 | 0 | 10000 | 0 |  |  | 0 | 0 |  |  | (Column D + E)
Material | 06410 | 1st Floor: Wood Cabinetry | 4500 | 0% | 0 | 0 | 4500 | 0 |  |  | 0 | 0 |  | Total Retainage (Line 5a + 5b or
Labor | 06410 | 1st Floor: Wood Cabinetry | 2500 | 0% | 0 | 0 | 2500 | 0 |  |  | 0 | 0 |  | Total in Column 1) …………………………… |  |  |  | 0
Material | 06410 | 1st Floor: Countertops | 1800 | 0% | 0 | 0 | 1800 | 0 |  |  | 0 | 0 |  | 6. TOTAL EARNED LESS RETAINAGE …………………. |  |  |  | 0
Labor | 06410 | 1st Floor: Countertops | 1200 | 0% | 0 | 0 | 1200 | 0 |  |  | 0 | 0 |  |  | (Line 4 less Line 5 Total)
Material | 06410 | 2nd Floor: Lavatory Countertops | 27000 | 0% | 0 | 0 | 27000 | 0 |  |  | 0 | 0 |  | 7. TOTAL PREVIOUS CERTIFICATES FOR PAYMENT |  |  |  | 0
Labor | 06410 | 2nd Floor: Lavatory Countertops | 8000 | 0% | 0 | 0 | 8000 | 0 |  |  | 0 | 0 |  |  | (Line 6 from prior Requistion)………………
Material | 06410 | 3rd Floor: Wood Cabinetry | 27000 | 0% | 0 | 0 | 27000 | 0 |  |  | 0 | 0 |  | 8. CURRENT PAYMENT DUE …………………………………. |  |  |  | 0
Labor | 06410 | 3rd Floor: Wood Cabinetry | 11000 | 0% | 0 | 0 | 11000 | 0 |  |  | 0 | 0 |  | 9. BALANCE TO FINISH, PLUS RETAINAGE ………………… |  |  |  | 996000
Material | 06410 | 3rd Floor: Countertops | 18000 | 0% | 0 | 0 | 18000 | 0 | Net by Change Orders |  | 0 |  |  |  | (Line 3 less Line 6)
Labor | 06410 | 3rd Floor: Countertops | 10000 | 0% | 0 | 0 | 10000 | 0 | SUB-CONTRACTOR AUTHORIZED OFFICER SIGNATURE: |  |  |  |  | GENERAL CONTRACTOR AUTHORIZED AMOUNT |  |  | _____________________
Material | 06410 | 3rd Floor: Closet interiors | 9000 | 0% | 0 | 0 | 9000 | 0 | BY: | Tomasz Bartosiak |  | Senior Project Manager |  |  | APPROVED BY: ______________________________________
Labor | 06410 | 3rd Floor: Closet interiors | 5000 | 0% | 0 | 0 | 5000 | 0 |  | Tomasz Bartosiak |  | TITLE
Material | 06410 | 4th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 4th Floor: Lavatory Countertops | 4000 | 0% | 0 | 0 | 4000 | 0
Material | 06410 | 4th Floor: Wood Cabinetry | 49500 | 0% | 0 | 0 | 49500 | 0
Labor | 06410 | 4th Floor: Wood Cabinetry | 20500 | 0% | 0 | 0 | 20500 | 0
Material | 06410 | 4th Floor: Countertops | 36000 | 0% | 0 | 0 | 36000 | 0
Labor | 06410 | 4th Floor: Countertops | 19000 | 0% | 0 | 0 | 19000 | 0
Material | 06410 | 4th Floor: Closet interiors | 18000 | 0% | 0 | 0 | 18000 | 0
Labor | 06410 | 4th Floor: Closet interiors | 7000 | 0% | 0 | 0 | 7000 | 0
Material | 06410 | 4th Floor: Benches | 9000 | 0% | 0 | 0 | 9000 | 0
Labor | 06410 | 4th Floor: Benches | 3000 | 0% | 0 | 0 | 3000 | 0
Material | 06410 | 5th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 5th Floor: Lavatory Countertops | 4000 | 0% | 0 | 0 | 4000 | 0
Material | 06410 | 5th Floor: Wood Cabinetry | 49500 | 0% | 0 | 0 | 49500 | 0
Labor | 06410 | 5th Floor: Wood Cabinetry | 20500 | 0% | 0 | 0 | 20500 | 0
Material | 06410 | 5th Floor: Countertops | 31500 | 0% | 0 | 0 | 31500 | 0
Labor | 06410 | 5th Floor: Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Material | 06410 | 5th Floor: Closet interiors | 18000 | 0% | 0 | 0 | 18000 | 0
Labor | 06410 | 5th Floor: Closet interiors | 7000 | 0% | 0 | 0 | 7000 | 0
Material | 06410 | 5th Floor: Benches | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 5th Floor: Benches | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 6th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 6th Floor: Lavatory Countertops | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 6th Floor: Wood Cabinetry | 31500 | 0% | 0 | 0 | 31500 | 0
Labor | 06410 | 6th Floor: Wood Cabinetry | 13500 | 0% | 0 | 0 | 13500 | 0
Material | 06410 | 6th Floor: Countertops | 18000 | 0% | 0 | 0 | 18000 | 0
Labor | 06410 | 6th Floor: Countertops | 7000 | 0% | 0 | 0 | 7000 | 0
Material | 06410 | 6th Floor: Closet interiors | 9000 | 0% | 0 | 0 | 9000 | 0
Labor | 06410 | 6th Floor: Closet interiors | 6000 | 0% | 0 | 0 | 6000 | 0
Material | 06410 | 6th Floor: Benches | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 6th Floor: Benches | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 7th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 7th Floor: Lavatory Countertops | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 7th Floor: Wood Cabinetry | 28800 | 0% | 0 | 0 | 28800 | 0
Labor | 06410 | 7th Floor: Wood Cabinetry | 13200 | 0% | 0 | 0 | 13200 | 0
Material | 06410 | 7th Floor: Countertops | 16200 | 0% | 0 | 0 | 16200 | 0
Labor | 06410 | 7th Floor: Countertops | 6800 | 0% | 0 | 0 | 6800 | 0
Material | 06410 | 7th Floor: Closet interiors | 9000 | 0% | 0 | 0 | 9000 | 0
Labor | 06410 | 7th Floor: Closet interiors | 6000 | 0% | 0 | 0 | 6000 | 0
Material | 06410 | 7th Floor: Benches | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 7th Floor: Benches | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 8th Floor: Lavatory Countertops | 13500 | 0% | 0 | 0 | 13500 | 0
Labor | 06410 | 8th Floor: Lavatory Countertops | 3500 | 0% | 0 | 0 | 3500 | 0
Material | 06410 | 8th Floor: Benches | 18000 | 0% | 0 | 0 | 18000 | 0
Labor | 06410 | 8th Floor: Benches | 4500 | 0% | 0 | 0 | 4500 | 0
|  | Total For 06410: | 880000 | 0% | 0 | 0 | 880000 | 0
|  | Line Totals | 996000 | 0% | 0 | 0 | 996000 | 0
REVISED: Cells shaded red (E16:E79) were adjusted — each Material line reduced 10%, with that amount added to its paired Labor line. Contract total unchanged at $996,000.00. Hover any red cell for the original amount.
11250
Contract Value
450000
Material |  | Labor
364500 |  | 67500
81.1749
81.1749
Note on E16: Peter Ligas: REVISED: Material -10% (was $40,000). $4,000 moved to Labor E17.
Note on E17: Peter Ligas: REVISED: Labor +$4,000 (was $10,000), shifted from Material E16.
Note on E18: Peter Ligas: REVISED: Material -10% (was $15,000). $1,500 moved to Labor E19.
Note on E19: Peter Ligas: REVISED: Labor +$1,500 (was $2,500), shifted from Material E18.
Note on E20: Peter Ligas: REVISED: Material -10% (was $5,000). $500 moved to Labor E21.
Note on E21: Peter Ligas: REVISED: Labor +$500 (was $1,000), shifted from Material E20.
Note on E22: Peter Ligas: REVISED: Material -10% (was $50,000). $5,000 moved to Labor E23.
Note on E23: Peter Ligas: REVISED: Labor +$5,000 (was $5,000), shifted from Material E22.
Note on E24: Peter Ligas: REVISED: Material -10% (was $5,000). $500 moved to Labor E25.
Note on E25: Peter Ligas: REVISED: Labor +$500 (was $2,000), shifted from Material E24.
Note on E26: Peter Ligas: REVISED: Material -10% (was $2,000). $200 moved to Labor E27.
Note on E27: Peter Ligas: REVISED: Labor +$200 (was $1,000), shifted from Material E26.
Note on E28: Peter Ligas: REVISED: Material -10% (was $30,000). $3,000 moved to Labor E29.
Note on E29: Peter Ligas: REVISED: Labor +$3,000 (was $5,000), shifted from Material E28.
Note on E30: Peter Ligas: REVISED: Material -10% (was $30,000). $3,000 moved to Labor E31.
Note on E31: Peter Ligas: REVISED: Labor +$3,000 (was $8,000), shifted from Material E30.
Note on E32: Peter Ligas: REVISED: Material -10% (was $20,000). $2,000 moved to Labor E33.
Note on E33: Peter Ligas: REVISED: Labor +$2,000 (was $8,000), shifted from Material E32.
Note on E34: Peter Ligas: REVISED: Material -10% (was $10,000). $1,000 moved to Labor E35.
Note on E35: Peter Ligas: REVISED: Labor +$1,000 (was $4,000), shifted from Material E34.
Note on E36: Peter Ligas: REVISED: Material -10% (was $15,000). $1,500 moved to Labor E37.
Note on E37: Peter Ligas: REVISED: Labor +$1,500 (was $2,500), shifted from Material E36.
Note on E38: Peter Ligas: REVISED: Material -10% (was $55,000). $5,500 moved to Labor E39.
Note on E39: Peter Ligas: REVISED: Labor +$5,500 (was $15,000), shifted from Material E38.
Note on E40: Peter Ligas: REVISED: Material -10% (was $40,000). $4,000 moved to Labor E41.
Note on E41: Peter Ligas: REVISED: Labor +$4,000 (was $15,000), shifted from Material E40.
Note on E42: Peter Ligas: REVISED: Material -10% (was $20,000). $2,000 moved to Labor E43.
Note on E43: Peter Ligas: REVISED: Labor +$2,000 (was $5,000), shifted from Material E42.
Note on E44: Peter Ligas: REVISED: Material -10% (was $10,000). $1,000 moved to Labor E45.
Note on E45: Peter Ligas: REVISED: Labor +$1,000 (was $2,000), shifted from Material E44.
Note on E46: Peter Ligas: REVISED: Material -10% (was $15,000). $1,500 moved to Labor E47.
Note on E47: Peter Ligas: REVISED: Labor +$1,500 (was $2,500), shifted from Material E46.
Note on E48: Peter Ligas: REVISED: Material -10% (was $55,000). $5,500 moved to Labor E49.
Note on E49: Peter Ligas: REVISED: Labor +$5,500 (was $15,000), shifted from Material E48.
Note on E50: Peter Ligas: REVISED: Material -10% (was $35,000). $3,500 moved to Labor E51.
Note on E51: Peter Ligas: REVISED: Labor +$3,500 (was $10,000), shifted from Material E50.
Note on E52: Peter Ligas: REVISED: Material -10% (was $20,000). $2,000 moved to Labor E53.
Note on E53: Peter Ligas: REVISED: Labor +$2,000 (was $5,000), shifted from Material E52.
Note on E54: Peter Ligas: REVISED: Material -10% (was $15,000). $1,500 moved to Labor E55.
Note on E55: Peter Ligas: REVISED: Labor +$1,500 (was $2,000), shifted from Material E54.
Note on E56: Peter Ligas: REVISED: Material -10% (was $15,000). $1,500 moved to Labor E57.
Note on E57: Peter Ligas: REVISED: Labor +$1,500 (was $2,000), shifted from Material E56.
Note on E58: Peter Ligas: REVISED: Material -10% (was $35,000). $3,500 moved to Labor E59.
Note on E59: Peter Ligas: REVISED: Labor +$3,500 (was $10,000), shifted from Material E58.
Note on E60: Peter Ligas: REVISED: Material -10% (was $20,000). $2,000 moved to Labor E61.
Note on E61: Peter Ligas: REVISED: Labor +$2,000 (was $5,000), shifted from Material E60.
Note on E62: Peter Ligas: REVISED: Material -10% (was $10,000). $1,000 moved to Labor E63.
Note on E63: Peter Ligas: REVISED: Labor +$1,000 (was $5,000), shifted from Material E62.
Note on E64: Peter Ligas: REVISED: Material -10% (was $15,000). $1,500 moved to Labor E65.
Note on E65: Peter Ligas: REVISED: Labor +$1,500 (was $2,000), shifted from Material E64.
Note on E66: Peter Ligas: REVISED: Material -10% (was $15,000). $1,500 moved to Labor E67.
Note on E67: Peter Ligas: REVISED: Labor +$1,500 (was $2,000), shifted from Material E66.
Note on E68: Peter Ligas: REVISED: Material -10% (was $32,000). $3,200 moved to Labor E69.
Note on E69: Peter Ligas: REVISED: Labor +$3,200 (was $10,000), shifted from Material E68.
Note on E70: Peter Ligas: REVISED: Material -10% (was $18,000). $1,800 moved to Labor E71.
Note on E71: Peter Ligas: REVISED: Labor +$1,800 (was $5,000), shifted from Material E70.
Note on E72: Peter Ligas: REVISED: Material -10% (was $10,000). $1,000 moved to Labor E73.
Note on E73: Peter Ligas: REVISED: Labor +$1,000 (was $5,000), shifted from Material E72.
Note on E74: Peter Ligas: REVISED: Material -10% (was $15,000). $1,500 moved to Labor E75.
Note on E75: Peter Ligas: REVISED: Labor +$1,500 (was $2,000), shifted from Material E74.
Note on E76: Peter Ligas: REVISED: Material -10% (was $15,000). $1,500 moved to Labor E77.
Note on E77: Peter Ligas: REVISED: Labor +$1,500 (was $2,000), shifted from Material E76.
Note on E78: Peter Ligas: REVISED: Material -10% (was $20,000). $2,000 moved to Labor E79.
Note on E79: Peter Ligas: REVISED: Labor +$2,000 (was $2,500), shifted from Material E78.