## BPL CP2 - PROJECT
Project_Name | Project_Number | GC_Name | GC_Contact | Address | Start_Date | End_Date | Stage
Brooklyn Public Library - CP2 | 30400 | Gilbane Building Company | FGaudio@GilbaneCo.com | 88 Pine Street, 27th Floor, NY NY 10005 | 2025-09-06 | 2027-10-21 | Submitals

## BPL CP2 - PRIME_CONTRACTS
Contract_ID | GC_Name | GC_Contact_Name | GC_Contact_Email | GC_Contact_Phone | Original_Contract_Value | Start_Date | End_Date | Payment_Terms (e.g. Net 30, Net 60) | Contract Document Link (OneDrive URL) | Contract Scheduled Document Link (OneDrive or PDF)
J10297.200-0004-000 | Gilbane Building Company | Frank Gaudio | FGaudio@GilbaneCo.com | 516-592-8208 | 3676024.48 | 2025-09-06 | 2027-10-21 | Net 90 | https://www.dropbox.com/scl/fo/m09jrtziezzi79516yg7d/AEbOW6pSfV0F5iVjtvjbzSA/BPL%20CP-2/BPL%20CP2.pdf?rlkey=2gle93ap7ug1j7ugx22xk0pxj&st=oz0ll7u4&dl=0 | https://www.dropbox.com/scl/fo/m09jrtziezzi79516yg7d/AEbw8dRfaHe7DYf7UnKYHWg/BPL%20CP-2/BPL%20II%20May%20Schedule%20Update%206.11.25.pdf?rlkey=2gle93ap7ug1j7ugx22xk0pxj&st=g3ofux93&dl=0

## BPL CP2 - PRIME_COs
CO_ID | Name | Description | Status | Amount (auto) | Reason | Schedule_Impact_Days | Markup_Pct (e.g. 10 = 10%) | Total_CO_Amount (auto) | Creator | Assignee | Due_Date | Approval_Date | Document_Link
30400-0001 |  | Fabrication and Installation of Shelves in PA 5 | Approved | -16793.97 |  |  |  | -16793.97 |  |  | 2025-06-24 | 2025-10-17
30400-0002 |  | Add Alternate Proposal-Fabrication and Installation of Arches | VOID | 598606.82 |  |  |  | 598606.82 |  |  | 2025-06-17
30400-0003 |  | Bulletin #1 Change Order-CP2 | Pending | 297790 |  |  |  | 297790 |  |  | 2025-06-17
30400-0004 |  | Installation of New Bookcase Backing and Wooden Base in Project Area 5 | Pending | 157488.54 |  |  |  | 157488.54 |  |  | 2025-10-17
30400-0005 |  | Bulletin #2-Fabrication and Installation of Plain Sawn White Oak Base in CP-2 | Pending | 9196.67 |  |  |  | 9196.67 |  |  | 2025-07-11

## BPL CP2 - PRIME_CO_LINE_ITEMS
CO_ID | Category | Cost_Code | Item | Qty | Unit_Type | Unit_Price | Price (Qty × Unit_Price)
30400-0001 |  |  | Fabrication and Installation of Shelves in PA 5 | 1 | LS | -16793.97 | -16793.97
30400-0002 |  |  | Add Alternate Proposal-Fabrication and Installation of Arches | 1 | LS | 598606.82 | 598606.82
30400-0003 |  |  | Bulletin #1 Change Order-CP2 | 1 | LS | 297790 | 297790
30400-0004 |  |  | Installation of New Bookcase Backing and Wooden Base in Project Area 5 | 1 | LS | 157488.54 | 157488.54
30400-0005 |  |  | Bulletin #2-Fabrication and Installation of Plain Sawn White Oak Base in CP-2 | 1 | LS | 9196.67 | 9196.67

## BPL CP2 - RFQs
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Title | Vendor | Status | Final_Amount | Issued Date

## BPL CP2 - RFQ_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Item | Unit | Qty | Unit_Price

## BPL CP2 - RFQ_ATTACHMENTS
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Document_Name | Document_Link

## BPL CP2 - PURCHASE_ORDERS
PROJECT NUMBER | PROJECT NAME | PO_ID | Linked_RFQ_ID (optional) | Issue_Date | Status | Vendor | Trade | PO_Amount | Tax_Rate | Expected_Date | Delivery_Date | Payment_Terms (e.g. Net 30) | Lead_Time | Ship_To | Notes | Created_By | Document_Link
30400 | Brooklyn Public Library - CP2 | 25248 |  | 2025-08-25 | CLOSED | Tecticonism Studio | Civil | 2100 | [5 empty] | Ell NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Tomasz
30400 | Brooklyn Public Library - CP2 | 25353 |  | 2025-08-25 | CLOSED | Tecticonism Studio | Civil | 4630 |  | 2025-07-03 | 2025-07-03 |  |  | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Tomasz
30400 | Brooklyn Public Library - CP2 | 25474 |  | 2025-08-25 |  | Ernest and Neuman Studios LLC | Civil | 150400 | [5 empty] | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Tomasz

## BPL CP2 - PO_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | PO_ID | Item | Qty | Unit | Unit_Price | Price (Qty × Unit_Price)
30400 | Brooklyn Public Library - CP2 | 25248 | Brooklyn Public Library PA 8B-Shop Drawings | 1 |  | 2100 | 2100
30400 | Brooklyn Public Library - CP2 | 25353 | BPL CP2 Shop Drawings (PA 5, 6, 10) | 1 |  | 4450 | 4450
30400 | Brooklyn Public Library - CP2 | 25353 | Consolidation of PA 10E & 10W in one set | 1 |  | 180 | 180
30400 | Brooklyn Public Library - CP2 | 25474 | Refinishing of PA 5-Excludes individual shelves back panels and benches | 1 |  | 51300 | 51300
30400 | Brooklyn Public Library - CP2 | 25474 | Refinishing of Project Area 6-Includes individual shelves, back panels, benches and stroller area as per detailed quote | 1 |  | 99100 | 99100

## BPL CP2 - PO_PAYMENTS
PROJECT NUMBER | PROJECT NAME | PO_ID | Date | CHK# | Note | Amount
30400 | Brooklyn Public Library - CP2 | 25248 | 2025-04-17 | AMEX-7022 | 75% Deposit - Paid Previously in PO 25188 | 656
30400 | Brooklyn Public Library - CP2 | 25248 | 2025-10-31 | AMEX-8020 | Final Payment | 656
30400 | Brooklyn Public Library - CP2 | 25353 | 2025-06-09 | PayPal-AMEX-8020 | Deposit (50%) | 2225
30400 | Brooklyn Public Library - CP2 | 25353 | 2025-08-21 |  | Final 50% Payment | 2225
30400 | Brooklyn Public Library - CP2 | 25353 | 2025-10-31 | AMEX-8020 | Final Payment | 180

## BPL CP2 - PO_CHANGE_ORDERS
PROJECT NUMBER | PROJECT NAME | PO_ID | PO_CO_ID | Name | Description | Status | Amount | Reason | Schedule_Impact_Days | Markup_Pct | Creator | Assignee | Due_Date | Approval_Date | Document_Link

## BPL CP2 - PO_CO_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | PO_CO_ID | Category | Cost_Code | Item | Qty | Unit_Type | Unit_Price | Price (Qty × Unit_Price)