## Korean - PROJECT
Project_Name | Project_Number | GC_Name | GC_Contact | Address | Start_Date | End_Date | Stage
JFK NTO Korean Air Lounge | 31200 | Holt Construction | Madelyne Grabowski | 50 East Washington Avenue Pearl River, NY 10965 | 2025-02-10 | 2026-06-15 | Submitals

## Korean - PRIME_CONTRACTS
Contract_ID | GC_Name | GC_Contact_Name | GC_Contact_Email | GC_Contact_Phone | Original_Contract_Value | Start_Date | End_Date | Payment_Terms (e.g. Net 30, Net 60) | Contract Document Link (OneDrive URL) | Contract Scheduled Document Link (OneDrive or PDF)
25-049.011 | Holt Construction | Madelyne Grabowski | mgrabowski@holtcc.com | 845-735-4054 | 1400000 | 2025-02-10 | 2026-06-15 | Net 90 | https://www.dropbox.com/scl/fo/m09jrtziezzi79516yg7d/APqaMYy6JupVpIEXekrtISQ/JFK%20Korean/JFK%20KOREAN.pdf?rlkey=2gle93ap7ug1j7ugx22xk0pxj&st=9tfyg4du&dl=0 | https://www.dropbox.com/scl/fo/m09jrtziezzi79516yg7d/ABPGg7zFOVsIyx7lD_ngLQI/JFK%20Korean/Sub%20Schedule%20-%2012-15-25.pdf?rlkey=2gle93ap7ug1j7ugx22xk0pxj&st=ld1hdjyc&dl=0

## Korean - PRIME_COs
CO_ID | Name | Description | Status | Amount (auto) | Reason | Schedule_Impact_Days | Markup_Pct (e.g. 10 = 10%) | Total_CO_Amount (auto) | Creator | Assignee | Due_Date | Approval_Date | Document_Link
31200-001A | Mockup review |  | Pending | 20000 |  |  |  | 20000 |  |  | 2025-12-16
31200-001B | Mockup review including delivery to job site |  | Pending | 24242.12 |  |  |  | 24242.12 |  |  | 2025-12-16
31200-0002 | Miller Lounge 309 BQ-3 via BQ-2 |  | Pending | 10122.3 |  |  |  | 10122.3 |  |  | 2025-12-16
31200-003 | Credit#1 Fixed Table Metal Supports and Countertops | Credit#1 Fixed Table Metal Supports and Countertops | Pending | -48645 |  |  |  | -48645

## Korean - PRIME_CO_LINE_ITEMS
CO_ID | Category | Cost_Code | Item | Qty | Unit_Type | Unit_Price | Price (Qty × Unit_Price)
31200-001A |  |  | Mockup review | 1 | LS | 20000 | 20000
31200-001B |  |  | Mockup review including delivery to job site | 1 | LS | 24242.12 | 24242.12
31200-0002 |  |  | Miller Lounge 309 BQ-3 via BQ-2 | 1 | LS | 10122.3 | 10122.3
31200-003 |  |  | Credit#1 Fixed Table Metal Supports and Countertops | 1 | LS | -48645 | -48645

## Korean - RFQs
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Title | Vendor | Status | Final_Amount | Issued Date
31200 | JFK NTO Korean Air Lounge | RFQ-2025-1616 | Solid Plain Sliced Walnut Lumber Supply | Holt & Bugbee / Lenoble Lumber

## Korean - RFQ_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Item | Unit | Qty | Unit_Price
31200 | JFK NTO Korean Air Lounge | RFQ-2025-1616 | Solid Plain Sliced Walnut |  | 2

## Korean - RFQ_ATTACHMENTS
PROJECT NUMBER | PROJECT NAME | RFQ_ID | Document_Name | Document_Link
31200 | JFK NTO Korean Air Lounge | RFQ-2025-1616

## Korean - PURCHASE_ORDERS
PROJECT NUMBER | PROJECT NAME | PO_ID | Linked_RFQ_ID (optional) | Issue_Date | Status | Vendor | Trade | PO_Amount | Tax_Rate | Expected_Date | Delivery_Date | Payment_Terms (e.g. Net 30) | Lead_Time | Ship_To | Notes | Created_By | Document_Link
31200 | JFK NTO Korean Air Lounge | 25741 |  | 2025-08-25 | OPEN | Woodwork Shop Drawings LLC | Civil | 2225 | [5 empty] | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Sebastian
31200 | JFK NTO Korean Air Lounge | 25761 |  | 2025-08-25 | CLOSED | Holt and Bugbee | Civil | 272.1 | [5 empty] | Elli NY Design | Please advise minimum 1 day before delivery to ensure Loading Dock availability. . | Sebastian
31200 | JFK NTO Korean Air Lounge | 25764 |  | 2025-08-25 | CLOSED | SWAC | Civil | 1000 |  |  | 2025-10-20 |  |  | Elli NY Design | Please advise minimum 1 day before delivery to ensure Loading Dock availability. | Tomasz
31200 | JFK NTO Korean Air Lounge | 25775 |  | 2025-08-25 | CLOSED | Atlantic Plywood | Civil | 178.68 | [5 empty] | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Sebastian
31200 | JFK NTO Korean Air Lounge | 25819 |  | 2025-11-11 | CLOSED | Hi-Tech Metals MFG, LLC | Civil | 500 | [5 empty] | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Sebastian
31200 | JFK NTO Korean Air Lounge | 26080 |  | 2025-08-25 | OPEN | Facility Concepts Inc | Civil | 16654.79 |  |  | 2026-03-16 |  |  | Elli NY Design | Please advise minimuin 1 day before delivery to ensure Loading Dock availability | Sebastian

## Korean - PO_LINE_ITEMS
PROJECT NUMBER | PROJECT NAME | PO_ID | Item | Qty | Unit | Unit_Price | Price (Qty × Unit_Price)
31200 | JFK NTO Korean Air Lounge | 25741 | Shop drawings set – millwork shop drawings for JFK T1 Korean Airlines per your request. Includes 1 revision per Elli and 2 per architect notes. 18 days of work. | 1 | LS | 2225 | 2225
31200 | JFK NTO Korean Air Lounge | 25761 | D2S 1" 5/4 FAS KD WALNUT, 6"+W X 2P/7-8' | 14 | BF | 17.65 | 247.1
31200 | JFK NTO Korean Air Lounge | 25761 | Delivery Charge | 1 | LS | 25 | 25
31200 | JFK NTO Korean Air Lounge | 25764 | Secure worker | 1 | LS | 1000 | 1000
31200 | JFK NTO Korean Air Lounge | 25775 | 3/4 4x8 A1 PS WALNUT SMN MDF | 1 | SHT | 143.68 | 143.68
31200 | JFK NTO Korean Air Lounge | 25775 | Handling-APC (as per Quote 6783263-00) | 1 | LS | 35 | 35
31200 | JFK NTO Korean Air Lounge | 25819 | Samples of 1” round steel tubes and powder coating finish PPB-8034 Melted Bronze | 1 | LS | 500 | 500
31200 | JFK NTO Korean Air Lounge | 26080 | CUSTOM LOUNGE BANQUETTE W/CABINETRY | 1 | EA | 15384.79 | 15384.79
31200 | JFK NTO Korean Air Lounge | 26080 | Crating & Packaging | 1 | LS | 295 | 295
31200 | JFK NTO Korean Air Lounge | 26080 | Freight (as per proposal #31155) | 1 | LS | 975 | 975

## Korean - PO_PAYMENTS
PROJECT NUMBER | PROJECT NAME | PO_ID | Date | CHK# | Note | Amount
31200 | JFK NTO Korean Air Lounge | 25741 | 2025-10-10 | 1141 | Payment Civil Check#1141 | 1500
31200 | JFK NTO Korean Air Lounge | 25741 | 2025-11-10 | 157 | Payment Civil Check#157 | 500
31200 | JFK NTO Korean Air Lounge | 25741 | 2025-12-12 | 1197 | Payment Civil Check#1197 | 1000
31200 | JFK NTO Korean Air Lounge | 25761 | 2025-12-12 | 1196 | Payment Civil Check#1196 | 272.1
31200 | JFK NTO Korean Air Lounge | 25764 | 2025-10-20 | Amex | Payment Amex | 1000
31200 | JFK NTO Korean Air Lounge | 25775 | 2025-12-12 | 1195 | Payment Civil Check#1195 | 178.68
31200 | JFK NTO Korean Air Lounge | 25819 | 2025-11-11 |  | Payment | 500

## Korean - PO_CHANGE ORDERSs
PROJECT NUMBER | PROJECT NAME | PO_ID | PO_CO_ID | Name | Description | Status | Amount | Reason | Schedule_Impact_Days | Markup_Pct | Creator | Assignee | Due_Date | Approval_Date | Document_Link
31200 | JFK NTO Korean Air Lounge | 25741 | 25741-01 | CO25741-01 Millwork Shop Drawings | Millwork shop drawings for JFK T1 Korean Airlines additional benches | APPROVED | 775 | [5 empty] | 2025-10-22
31200 | JFK NTO Korean Air Lounge | 25741 | 25741-02 | CO25741-02 Additional Revisions | To make additional revisions/changes and change scale to all drawings for this project per your request | APPROVED | 1300 | [5 empty] | 2026-01-23

## Korean - PO_CO_LINE ITEMs
PROJECT NUMBER | PROJECT NAME | PO_CO_ID | Category | Cost_Code | Item | Qty | Unit_Type | Unit_Price | Price (Qty × Unit_Price)
31200 | JFK NTO Korean Air Lounge | 25741-01 | Services | — | Millwork shop drawings for JFK T1 Korean Airlines additional benches | 1 | LS | 775 | 775
31200 | JFK NTO Korean Air Lounge | 25741-02 | Services | — | Additional revisions/changes and change scale to all drawings for this project per your request | 1 | LS | 1300 | 1300